# Smart Parking Platform — Project Document

Prepared by: $oftware ¢orp.
Course: CIS 4374 — Software Project Management
Author: Dinh Pham
Document version: 1.5
Date: October 15, 2026

## Document Control

| Version | Date | Author | Summary of changes |
| --- | --- | --- | --- |
| 1.0 | 2026-09-10 | D. Pham | Initial release. Added existing software landscape, Vision & Scope, and first SRS draft with 22 use cases. |
| 1.1 | 2026-09-17 | D. Pham | Added Work Breakdown Structure (Section 5) and draft project timeline with Gantt chart (Section 6), scheduled within the Fall 2026 semester constraint. |

Table of Contents

Document Control	1

1. Introduction	4

2. Existing Software Landscape (Research)	4

2.1 Purpose of the Research	4

2.2 Market Overview	4

2.3 Competitor Analysis	4

2.4 Common Weaknesses in Current Solutions	5

2.5 How Our Platform Will Be Different	6

3. Vision and Scope	6

3.1 About $oftware ¢orp.	6

3.2 How This Project Was Acquired	7

3.3 Business Need	7

3.4 Vision Statement	7

3.5 Business Objectives and Success Metrics	7

3.6 Project Overview	8

3.7 Scope — In and Out	8

3.8 Stakeholders	9

3.9 Constraints and Assumptions	9

4. Software Requirements Specification (Draft)	10

4.1 Purpose and Scope of the SRS	10

4.2 Definitions and Acronyms	10

4.3 Actors	10

4.4 Use Cases	10

4.5 Non-Functional Requirements	14

4.6 External Interfaces	15

4.7 Requirements Traceability Matrix	15

4.8 Open Items for Future Versions	17

5. Work Breakdown Structure	17

5.1 Purpose and Approach	17

5.2 WBS Structure	17

5.3 WBS Dictionary (Level 2)	20

5.4 Decomposition Notes	21

6. Draft Project Timeline	21

6.1 Scheduling Approach and Assumptions	21

6.2 Phase Schedule	21

6.3 Milestones	22

6.4 Gantt Chart	23

6.5 Critical Path	24

6.6 Effort Estimates by Work Package	24

6.7 Open Scheduling Items	25

7. Product Backlog and Sprint 1 Plan	25

7.1 Approach	25

7.2 Epic Overview	26

7.3 Backlog — Login and Accounts	26

7.4 Backlog — User Interface	27

7.5 Backlog — Backend Processes	28

7.6 Backlog — Reporting and Analytics	29

7.7 Sprint 1 Plan	30

7.8 Acceptance Criteria — Sprint 1	32

7.9 Product Backlog Board	32

7.10 Open Backlog Items	33

8. Risk Management and Communication Plan	34

8.1 Risk Management Approach	34

8.2 Risk Identification by Category	34

8.3 Risk Register	37

8.4 Probability and Impact Matrix	39

8.5 Risk Triggers	39

8.6 Expected Monetary Value — Financial Risks	40

8.7 Communication Plan	41

8.8 Stakeholder Communication Matrix	43

8.9 Open Risk Management Items	44

9. Resource and Cost Plan	44

9.1 Approach	44

9.2 Roles and Resources	45

9.3 Cost Plan — Bottom-Up	47

9.4 Budgeted Cashflow	48

9.5 RACI Matrix	50

9.6 Earned Value Baseline	51

9.7 Open Resource and Cost Items	53

10. Next Steps	53

11. References	53

## 1. Introduction

This document is the living project document for the Smart Parking Platform. It is updated every week as the course moves through the project management life cycle. Version 1.0 covers three things: research into what already exists, the first draft of the Vision and Scope, and the first draft of the Software Requirements Specification (SRS).

The Smart Parking Platform is a web and mobile system that helps drivers find, reserve, and pay for parking spaces in parking garages in real time. It also gives parking operators tools to monitor occupancy, set pricing, and report on how their assets are used.

## 2. Existing Software Landscape (Research)

### 2.1 Purpose of the Research

Before writing requirements, we need to know what is already on the market. This tells us three things: which features drivers already expect, which problems are still unsolved, and where we can build something better. Everything in this section feeds into the differentiation strategy in Section 2.5 and the scope decisions in Section 3.7.

### 2.2 Market Overview

Smart parking is an established and growing market, not an empty one. Industry estimates put the smart parking platform market at roughly $3.9 billion in 2024, growing at about 12% per year. The named leaders in that research are ParkMobile, PayByPhone, SpotHero, ParkWhiz, INRIX, Passport, Flowbird, and hardware-side vendors such as Siemens, Bosch, and Cleverciti.

The market splits into four rough groups:

| Group | What they do | Examples |
| --- | --- | --- |
| Garage reservation apps | Book and prepay an off-street space in advance | SpotHero, ParkWhiz |
| Meter and session payment apps | Pay for on-street or municipal parking by the hour | ParkMobile, PayByPhone, Passport |
| Parking information and mapping | Show prices, rules, and locations without booking | Parkopedia, SpotAngels, BestParking |
| Operator-side management software | Gate control, occupancy tracking, revenue reporting | TIBA, Flowbird, Arivo, Parking.com |

The key finding is that no single product covers all four groups well. Drivers who want to reserve a garage use one app, drivers who want to pay a meter use another, and the garage operator often runs a third system that does not talk to either.

### 2.3 Competitor Analysis

| Competitor | Main strength | Main weakness | Gap we can use |
| --- | --- | --- | --- |
| SpotHero | Strongest brand in garage reservations; wide US coverage; clear prepay pricing; no separate booking fee | Prices carry a hidden margin; users report surge pricing gaps and garage access-code problems at the gate | Reliable, verified gate entry and transparent pricing |
| ParkWhiz (owned by Arrive) | Strong at venue, airport, and event parking; good prepay discounts | Users report reservations not honored at the garage and slow refunds | Guaranteed-space enforcement backed by live inventory |
| ParkMobile (owned by EasyPark Group) | Largest US footprint by zone coverage; very high app store rating volume | Focused on meter sessions, not garage reservation; per-transaction convenience fee; “phantom session” complaints | Combined reserve-and-pay in one flow, no per-transaction fee |
| PayByPhone | Official meter partner in many cities; simple session model | City-specific outages; late expiration alerts; almost no reservation capability | Dependable notification engine and session extension |
| Passport | Deep in smaller cities and university campuses | Crashes during payment; confusing zone numbering | Simpler, map-first space selection instead of zone codes |
| Parkopedia / SpotAngels | Very large database of prices and street rules; strong free-parking discovery | Information only — you generally cannot reserve or guarantee a space | Turn information into a guaranteed booking |
| Operator software (TIBA, Flowbird, Arivo) | Real gate hardware integration, occupancy counting, revenue reports | Sold to operators, not to drivers; little to no consumer-facing demand generation | One platform serving both sides with shared live data |

### 2.4 Common Weaknesses in Current Solutions

Reading across the competitor set, five problems repeat:

- Availability is predicted, not proven. Most consumer apps sell a spot based on an allocation the operator gave them, not on a live count of cars in the garage. This is the root cause of the “reservation not honored” complaint pattern.

- The two sides are disconnected. The driver app and the operator’s garage system are usually separate products from separate vendors. Data has to be reconciled manually.

- Pricing is not transparent. Convenience fees, dynamic markups, and drive-up-versus-prepay differences make it hard for a driver to know the real total.

- Entry at the gate is fragile. Access codes, QR codes, and license plate reading fail often enough that it is a top complaint category.

- Operators get reports, not insight. Occupancy numbers are common; pricing recommendations and demand forecasting are rare.

### 2.5 How Our Platform Will Be Different

Our platform is not trying to out-market SpotHero. It is trying to remove the root causes above. Four points of differentiation:

1. One platform, both sides, one source of truth. Competitors serve either drivers or operators. We serve both on shared live data. When a car enters a garage, the count changes for the operator dashboard and the driver map at the same instant. This directly attacks weakness 1 and 2.

2. Verified availability, not estimated availability. Availability comes from the operator’s live occupancy feed and from our own reservation ledger, not from a static block of spaces. If we show a space, it exists. Any reservation we cannot honor triggers an automatic refund plus a comparable alternate space nearby.

3. Honest total pricing. The price shown on the map is the price charged. Taxes and any operator fees are itemized before the user confirms. No separate per-transaction convenience fee.

4. Reservation and payment in one flow, with reliable entry. One flow covers search, reserve, pay, navigate, and enter. Entry supports both a dynamic QR pass and license plate recognition as a fallback, so a single failure does not strand the driver at the gate.

A fifth, longer-term differentiator is analytics that recommend, not just report — suggesting price changes to operators based on observed demand. This is planned but out of scope for the first release (see Section 3.7).

## 3. Vision and Scope

### 3.1 About $oftware ¢orp.

$oftware ¢orp. is a software development studio that builds platform products for the transportation and mobility sector. The studio works in cross-functional delivery teams and takes projects from requirements gathering through release and support. For this engagement the studio has committed six teams: Mobile Application, Web Application, Backend/API, Mapping & Location Services, Payment Integration, and Quality Assurance & Testing.

For the purposes of this course, $oftware ¢orp. is a fictitious company operating with an unlimited theoretical development budget. This removes cost as a constraint but does not remove the schedule constraint — the semester timeline is fixed.

### 3.2 How This Project Was Acquired

A regional parking operator group, together with a municipal transportation department, issued a request for proposal for a real-time parking reservation and management platform. Their existing setup used three separate vendors: one consumer booking app, one gate and access control system, and one spreadsheet-based revenue reporting process. The three did not share data, which caused oversold garages and monthly reconciliation work.

$oftware ¢orp. was invited to bid based on prior mobility platform work. Our proposal argued that the real problem was not a missing app but a missing single source of truth between the driver and the garage. The client accepted that framing, and the contract was awarded to $oftware ¢orp. as a full platform build covering both the driver-facing product and the operator-facing product.

The client’s stated priorities, in their order: 1. Never sell a space that is not actually available. 2. Give operators live visibility into occupancy and revenue. 3. Make the driver experience fast enough that it beats circling the block.

### 3.3 Business Need

Drivers spend a large share of their trip time searching for parking. That searching creates traffic congestion, wasted fuel, driver frustration, and lost productivity. On the other side, parking operators cannot see their own occupancy in real time, so they cannot price dynamically, cannot plan for events, and cannot tell which assets are underused.

Both problems come from the same missing piece: there is no shared, live, trusted picture of which spaces are open right now.

### 3.4 Vision Statement

For drivers and parking facility operators who waste time and revenue because parking availability is unknown until you arrive, the Smart Parking Platform is a web and mobile parking reservation and management platform that shows verified real-time availability, guarantees the reserved space, and gives operators live occupancy and pricing control. Unlike SpotHero, ParkWhiz, and ParkMobile, which serve only the driver and rely on allocated blocks of spaces, our product runs both sides of the transaction on one live inventory, so what the driver sees is what the operator actually has.

### 3.5 Business Objectives and Success Metrics

| ID | Objective | Success metric (target for first release) |
| --- | --- | --- |
| BO-1 | Cut the time drivers spend searching for parking | Median search-to-reserved time under 90 seconds |
| BO-2 | Eliminate unhonored reservations | Fewer than 0.5% of reservations fail at the gate |
| BO-3 | Increase garage utilization for operators | 10% increase in average occupancy at participating garages |
| BO-4 | Give operators live visibility | Occupancy dashboard reflects gate events within 30 seconds |
| BO-5 | Build driver trust in pricing | Zero difference between quoted total and charged total |

### 3.6 Project Overview

The platform has four parts:

- Mobile application (iOS and Android) — the main driver experience: map, search, reserve, pay, navigate, enter.

- Web application — the same driver features in a browser, plus the operator dashboard.

- Backend / API — accounts, inventory, reservations, pricing, notifications, and the shared source of truth.

- Integrations — mapping and navigation services, payment processors, and garage gate/occupancy hardware.

### 3.7 Scope — In and Out

In scope for the first release

- User registration, authentication, and vehicle profiles

- Real-time garage availability on an interactive map

- Search, filter, and compare garages by price, distance, and availability

- Reservation creation, extension, and cancellation

- Digital payment processing and refunds

- Digital entry pass (QR) with license plate recognition fallback

- Reservation history and downloadable receipts

- Push and email notifications and alerts

- Operator dashboard: listings, capacity, pricing, live occupancy

- Occupancy and revenue reporting for operators

- Integration with external mapping and navigation services

- Administrative tools for user management and dispute resolution

Out of scope for the first release (candidates for later releases)

- On-street and metered parking (garages only for now)

- Peer-to-peer or residential driveway rental

- Automated dynamic pricing recommendations

- EV charging reservation and billing

- Valet services

- Monthly and corporate permit management

- Transit ticketing bundles

Scope decisions in this section are provisional and will be refined during stakeholder analysis.

### 3.8 Stakeholders

| Stakeholder | Interest in the project | Influence |
| --- | --- | --- |
| Drivers / vehicle owners | Find and guarantee parking quickly at a fair price | High (end users) |
| Parking facility operators | Higher utilization, live occupancy, pricing control | High (paying client) |
| City transportation departments | Less congestion, compliance with city ordinance | Medium (regulatory) |
| System administrators | Stable operations, manageable support load | Medium |
| Finance and billing personnel | Accurate payouts, reconciliation, tax handling | Medium |
| Mobile application users | Fast, reliable app that works at the gate | High |
| Third-party payment providers | Compliant, low-fraud transaction volume | Medium (external dependency) |
| $oftware ¢orp. delivery teams | Clear requirements, workable schedule | High (delivery) |

### 3.9 Constraints and Assumptions

Constraints

- C-1: Unlimited theoretical development budget, but a fixed semester timeline.

- C-2: The platform depends on third-party services and APIs (mapping, payments, gate hardware) that we do not control.

- C-3: The system must comply with security and privacy requirements, city ordinances, and applicable laws.

- C-4: Payment handling must meet PCI DSS requirements.

Assumptions

- A-1: Participating garages can supply a live occupancy signal, or will accept our sensor/gate integration.

- A-2: Operators will keep their listing and pricing data current.

- A-3: Drivers have a smartphone with data service and location access at the time of booking.

- A-4: Mapping and payment providers will remain available under commercial terms.

## 4. Software Requirements Specification (Draft)

Status: Draft, version 1.0. This SRS will grow through the semester. Use cases here are written at a summary level; detailed flows, alternate flows, and acceptance criteria will be expanded in later versions.

### 4.1 Purpose and Scope of the SRS

This SRS describes what the Smart Parking Platform must do. It is written for the $oftware ¢orp. delivery teams, the QA team, and the client stakeholders who will approve the requirements. It covers the driver-facing web and mobile applications, the operator dashboard, and the backend services that support them.

### 4.2 Definitions and Acronyms

| Term | Meaning |
| --- | --- |
| Driver | An end user who searches for, reserves, and pays for parking |
| Operator | A person or company that manages one or more parking garages |
| Space | An individual parking spot inside a garage |
| Reservation | A confirmed, paid claim on a space for a defined time window |
| Entry pass | The credential used to open the gate (QR code or license plate) |
| LPR | License Plate Recognition |
| SRS | Software Requirements Specification |
| PCI DSS | Payment Card Industry Data Security Standard |

### 4.3 Actors

| Actor | Description |
| --- | --- |
| Guest | An unregistered visitor browsing availability |
| Driver | A registered end user |
| Operator | Manages garage listings, capacity, and pricing |
| Finance User | Handles payouts, refunds, and reconciliation |
| System Administrator | Manages accounts, permissions, and disputes |
| Payment Gateway | External payment processing service |
| Mapping Service | External mapping and navigation provider |
| Garage Hardware | Gate controllers, sensors, and LPR cameras |

### 4.4 Use Cases

#### UC-01 — Register Account

Actor: Guest Goal: Create an account so reservations can be made and saved. Preconditions: User is not registered. Main flow: User enters email, password, and name → system validates the input → system sends a verification email → user confirms → account is created. Alternate flow: Email already in use → system offers sign-in or password reset. Postcondition: A verified Driver account exists.

#### UC-02 — Authenticate (Log In / Log Out)

Actor: Driver, Operator, Finance User, System Administrator Goal: Access the account securely. Preconditions: A verified account exists. Main flow: User submits credentials → system verifies → session is created with the correct role permissions. Alternate flow: Wrong credentials three times → account is temporarily locked and a reset email is offered. Postcondition: Authenticated session, or access denied.

#### UC-03 — Manage Vehicle Profile

Actor: Driver Goal: Save vehicle details and license plate for gate entry. Preconditions: Driver is logged in. Main flow: Driver adds vehicle make, model, and plate number → system validates the plate format → vehicle is saved and can be set as default. Alternate flow: Duplicate plate on another account → flagged for administrator review. Postcondition: Vehicle is available for LPR entry and for reservations.

#### UC-04 — Search for Parking Near a Destination

Actor: Guest, Driver Goal: Find garages near a chosen address, landmark, or current location. Preconditions: Location access granted, or an address entered. Main flow: User enters a destination and an arrival/departure time → system queries live inventory → results are returned with distance, price, and available space count. Alternate flow: No garages within range → system widens the radius and shows the nearest option. Postcondition: A result set is displayed.

#### UC-05 — View Real-Time Availability on an Interactive Map

Actor: Guest, Driver Goal: See where open spaces are, visually. Preconditions: Search results exist. Main flow: System renders garage pins on the map → each pin shows price and live open space count → counts refresh as gate events arrive. Alternate flow: Live occupancy feed is unavailable → the garage is marked “availability estimated” and cannot be reserved as guaranteed. Postcondition: Driver can compare options at a glance.

#### UC-06 — Filter and Sort Results

Actor: Guest, Driver Goal: Narrow results to what actually fits the driver’s needs. Preconditions: Search results exist. Main flow: User applies filters (price ceiling, walking distance, covered parking, height clearance, accessible spaces, EV-adjacent) and sorts by price or distance. Alternate flow: Filters return zero results → system suggests which filter to relax. Postcondition: A filtered, sorted result set is displayed.

#### UC-07 — View Garage Details

Actor: Guest, Driver Goal: See full information before committing. Preconditions: A garage is selected. Main flow: System shows photos, address, hours, clearance, entry instructions, itemized pricing, and amenities. Postcondition: Driver has enough information to decide.

#### UC-08 — Reserve a Parking Space

Actor: Driver Goal: Hold a specific space for a specific time window. Preconditions: Driver is logged in; the garage reports verified availability. Main flow: Driver selects garage and time window → system places a temporary hold on a space → driver confirms → system proceeds to payment (UC-09). Alternate flow: The last space is taken during the hold → system releases the flow and offers the nearest comparable garage. Postcondition: A pending reservation exists, awaiting payment.

#### UC-09 — Pay for a Reservation

Actor: Driver, Payment Gateway Goal: Complete payment and confirm the reservation. Preconditions: A pending reservation exists. Main flow: Driver selects a saved or new payment method → system displays the itemized total → driver confirms → system sends the charge to the payment gateway → gateway approves → reservation is confirmed. Alternate flow: Payment declined → reservation hold is kept for 5 minutes and the driver may retry with another method. Postcondition: Reservation is confirmed and paid; the space is removed from live inventory.

#### UC-10 — Receive Booking Confirmation and Entry Pass

Actor: Driver Goal: Get proof of the reservation and the credential needed at the gate. Preconditions: Payment succeeded. Main flow: System issues a dynamic QR entry pass and registers the driver’s plate with the garage → confirmation is delivered in-app and by email. Alternate flow: Email delivery fails → the pass remains available in the app and by SMS. Postcondition: Driver holds a valid entry credential.

#### UC-11 — Navigate to the Garage

Actor: Driver, Mapping Service Goal: Get turn-by-turn directions to the reserved garage entrance. Preconditions: A confirmed reservation exists. Main flow: Driver taps “Navigate” → system hands the garage entrance coordinates to the mapping service → navigation begins. Alternate flow: Mapping service unavailable → system displays written directions and the entrance address. Postcondition: Driver is routed to the correct entrance, not just the building.

#### UC-12 — Enter the Garage

Actor: Driver, Garage Hardware Goal: Get through the gate without friction. Preconditions: A valid, currently active reservation exists. Main flow: LPR camera reads the plate and matches it to the reservation → gate opens → entry event is recorded and occupancy updates. Alternate flow 1: LPR fails → driver scans the QR pass at the reader. Alternate flow 2: Both fail → in-app support code opens the gate and an incident is logged. Postcondition: Driver is parked; occupancy count is updated everywhere.

#### UC-13 — Extend an Active Reservation

Actor: Driver Goal: Stay longer without getting towed or fined. Preconditions: An active reservation is in progress. Main flow: Driver requests extra time → system checks that the space is not booked by someone else → system quotes the additional charge → driver confirms and is charged. Alternate flow: The space is reserved by another driver for the later window → extension is refused, and the system offers to move the vehicle to another available space in the same garage. Postcondition: Reservation end time is updated, or the extension is denied with a clear reason.

#### UC-14 — Cancel a Reservation and Receive a Refund

Actor: Driver, Payment Gateway Goal: Cancel and get money back under the stated policy. Preconditions: A confirmed reservation exists that has not yet started. Main flow: Driver cancels → system applies the cancellation policy → refund is issued through the gateway → the space returns to live inventory. Alternate flow: Cancellation is inside the no-refund window → system states the policy and asks for confirmation before cancelling without refund. Postcondition: Reservation is cancelled; inventory and finances are consistent.

#### UC-15 — View Reservation History and Receipts

Actor: Driver Goal: Look up past parking and download receipts for expenses. Preconditions: Driver is logged in with at least one past reservation. Main flow: Driver opens history → system lists past and upcoming reservations → driver downloads a PDF receipt. Postcondition: Receipt is downloaded or emailed.

#### UC-16 — Receive Notifications and Alerts

Actor: Driver Goal: Be reminded before something goes wrong. Preconditions: Notifications are enabled. Main flow: System sends reservation confirmations, arrival reminders, expiration warnings before the reservation ends, and disruption alerts if a garage becomes unavailable. Alternate flow: Push notifications are disabled → system falls back to email or SMS. Postcondition: Driver is informed in time to act.

#### UC-17 — Manage Garage Listing and Capacity

Actor: Operator Goal: Keep the garage’s information and inventory correct. Preconditions: Operator account is verified and linked to a garage. Main flow: Operator edits address, hours, photos, clearance, total spaces, and reservable space count → system validates and publishes the changes. Alternate flow: Capacity is reduced below the number of existing reservations → system blocks the change and lists the affected reservations. Postcondition: Listing is live and consistent with existing reservations.

#### UC-18 — Set and Adjust Pricing

Actor: Operator Goal: Control what the garage charges by time and demand. Preconditions: Operator manages at least one garage. Main flow: Operator defines hourly and daily rates, time-of-day rules, and event pricing → system validates against city ordinance limits → new rates apply to future reservations only. Alternate flow: A proposed rate breaks a regulatory ceiling → change is rejected with an explanation. Postcondition: Pricing is updated; already-confirmed reservations are unaffected.

#### UC-19 — Monitor Live Occupancy Dashboard

Actor: Operator Goal: See what is happening in the garage right now. Preconditions: Operator is logged in; the garage has a live feed. Main flow: Dashboard displays current occupancy, spaces reserved versus walk-in, entries and exits, and revenue so far today, refreshing continuously. Alternate flow: Hardware feed drops → dashboard shows a stale-data warning with the last update time. Postcondition: Operator has an accurate live picture.

#### UC-20 — Generate Occupancy and Revenue Reports

Actor: Operator, Finance User Goal: Analyze utilization and revenue over a period. Preconditions: Historical data exists for the selected range. Main flow: User selects a date range and garages → system generates utilization rate, peak hours, average duration, and revenue → user exports to PDF or CSV. Alternate flow: Range exceeds retention limits → system caps the range and explains why. Postcondition: Report is generated and exported.

#### UC-21 — Process Operator Payouts

Actor: Finance User, Payment Gateway Goal: Pay operators their share on schedule. Preconditions: Completed, settled reservations exist for the payout period. Main flow: System calculates gross revenue minus platform fee and refunds per operator → Finance User reviews and approves → payout is sent through the gateway. Alternate flow: A discrepancy is found → the payout is held and flagged for reconciliation. Postcondition: Operators are paid and the payout is recorded.

#### UC-22 — Manage Users and Resolve Disputes

Actor: System Administrator Goal: Keep accounts healthy and settle problems fairly. Preconditions: Administrator is logged in with elevated permissions. Main flow: Administrator searches for an account, reviews reservation and entry logs, and takes action — issue a goodwill refund, correct a record, suspend an account, or resolve a duplicate plate claim. Alternate flow: The dispute involves a failed gate entry → administrator pulls the hardware incident log before deciding. Postcondition: The dispute is resolved and every action is written to an audit trail.

### 4.5 Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-1 | Performance | Map search results shall return within 2 seconds for 95% of requests. |
| NFR-2 | Performance | Availability counts shall reflect a gate event within 30 seconds. |
| NFR-3 | Availability | The platform shall maintain 99.9% uptime, measured monthly. |
| NFR-4 | Scalability | The system shall support 50,000 concurrent users without degrading NFR-1. |
| NFR-5 | Security | All traffic shall use TLS 1.3 or higher; passwords shall be stored hashed and salted. |
| NFR-6 | Security | Payment handling shall be PCI DSS compliant; the platform shall never store raw card numbers. |
| NFR-7 | Privacy | Location and plate data shall be retained only as long as needed and shall be deletable on user request. |
| NFR-8 | Usability | A first-time user shall complete search-to-reserved in under 90 seconds without help. |
| NFR-9 | Accessibility | Web and mobile interfaces shall meet WCAG 2.2 Level AA. |
| NFR-10 | Compatibility | The mobile app shall support the current and two prior major versions of iOS and Android. |
| NFR-11 | Reliability | A confirmed reservation that cannot be honored shall trigger an automatic refund and an alternate offer within 60 seconds. |
| NFR-12 | Auditability | All financial and administrative actions shall be written to an immutable audit log. |

### 4.6 External Interfaces

| Interface | Purpose | Notes |
| --- | --- | --- |
| Mapping / navigation API | Geocoding, map tiles, turn-by-turn routing to the garage entrance | External dependency; needs a fallback |
| Payment gateway | Authorization, capture, refunds, payouts | Must be PCI DSS compliant |
| Garage gate controllers | Open and close gates on valid credentials | Vendor-specific; adapter layer needed |
| Occupancy sensors / LPR cameras | Live space counts and plate reads | Accuracy affects NFR-2 and NFR-11 |
| Notification services | Push, email, SMS delivery | Multiple channels for fallback |

### 4.7 Requirements Traceability Matrix

Every use case in Section 4.4 is traced forward to the user stories that deliver it in Section 7 and to the Work Breakdown Structure branch that builds it in Section 5. The point of the matrix is to make two failures visible: a requirement nobody is building, and work nobody asked for.

| Use case | Name | User stories | WBS |
| --- | --- | --- | --- |
| UC-01 | Register Account | LOG-01, LOG-02, LOG-06, BE-01 | 1.3.2 |
| UC-02 | Authenticate | LOG-03, LOG-04, LOG-05, LOG-07, LOG-10, BE-02 | 1.3.2 |
| UC-03 | Manage Vehicle Profile | LOG-09 | 1.3.2 |
| UC-04 | Search for Parking | UI-02, UI-03, BE-18 | 1.6.2 |
| UC-05 | View Real-Time Availability | UI-01, BE-04a, BE-04b, BE-05a, BE-05b | 1.3.3 |
| UC-06 | Filter and Sort Results | UI-04, UI-05 | 1.4.2, 1.5.1 |
| UC-07 | View Garage Details | UI-06 | 1.5.1 |
| UC-08 | Reserve a Parking Space | UI-07, UI-09, BE-06, BE-07, BE-10a, BE-10b | 1.3.4 |
| UC-09 | Pay for a Reservation | UI-08, BE-12a, BE-12b | 1.7.2 |
| UC-10 | Confirmation and Entry Pass | UI-10, BE-17 | 1.8.4 |
| UC-11 | Navigate to the Garage | UI-11, BE-18 | 1.6.4 |
| UC-12 | Enter the Garage | BE-15a, BE-15b, BE-16a, BE-16b, BE-17 | 1.8.1 - 1.8.5 |
| UC-13 | Extend an Active Reservation | UI-14, BE-08 | 1.3.4.2 |
| UC-14 | Cancel and Receive a Refund | UI-15, BE-09 | 1.3.4.2, 1.7.3 |
| UC-15 | Reservation History and Receipts | UI-12, UI-13, RPT-11, RPT-12 | 1.4.4 |
| UC-16 | Notifications and Alerts | UI-16, BE-14 | 1.3.6 |
| UC-17 | Manage Listing and Capacity | UI-18, UI-20, BE-03 | 1.5.2.1 |
| UC-18 | Set and Adjust Pricing | UI-19, BE-11 | 1.3.5, 1.5.2.2 |
| UC-19 | Monitor Live Occupancy | UI-17, RPT-01 | 1.5.2.3 |
| UC-20 | Occupancy and Revenue Reports | RPT-02 - RPT-07 | 1.3.7, 1.5.2.4 |
| UC-21 | Process Operator Payouts | BE-13, RPT-08 | 1.7.4 |
| UC-22 | Manage Users and Resolve Disputes | LOG-08, UI-21, BE-19, RPT-09, RPT-10 | 1.5.3 |

Two observations from building it:

- Every use case has at least one story and one WBS branch. Nothing in Section 4 is unfunded.

- One story has no use case: BE-20, the deployment pipeline. That is correct rather than a gap. It is infrastructure the project needs in order to deliver anything, not behaviour a user asked for, so it traces to WBS 1.3.1 and to nothing in Section 4.

### 4.8 Open Items for Future Versions

These are known gaps in the current version and will be filled as the semester continues:

- Detailed alternate and exception flows for every use case

- Use case diagrams and sequence diagrams

- Data model and entity relationship diagram

- Acceptance criteria for the backlog beyond Sprint 1, written at each sprint’s grooming session — Sprint 1 is complete in Section 7.8

- Full stakeholder analysis and elicitation notes

Closed in version 1.5: the requirements traceability matrix is now Section 4.7, and the work breakdown structure, schedule, budget and risk register are Sections 5, 6, 9 and 8.

## 5. Work Breakdown Structure

### 5.1 Purpose and Approach

The Work Breakdown Structure (WBS) breaks the Smart Parking Platform into the actual pieces of work that have to be completed. It is deliverable-based, not activity-based: every item names something that gets produced, not something that gets done.

The structure is decomposed to at least three levels throughout, and to four levels where a work package needs more detail before it can be estimated. The rule used for stopping the decomposition was the 8/80 rule — a work package should be small enough to estimate in under 80 hours and large enough to be worth tracking, roughly 8 hours at minimum.

Each Level 2 branch maps to one of the six $oftware ¢orp. delivery teams named in Section 3.1, so ownership is clear before scheduling begins.

### 5.2 WBS Structure

1.0 Smart Parking Platform

1.1 Project Management

- 1.1.1 Project charter

- 1.1.2 Project management plan

- 1.1.3 Stakeholder register and communication plan

- 1.1.4 Weekly status reporting and stakeholder updates

- 1.1.5 Risk register and risk reviews

- 1.1.6 Change control log

- 1.1.7 Project closeout and lessons learned

1.2 Requirements and Design

- 1.2.1 Stakeholder analysis

- 1.2.2 Requirements elicitation

  - 1.2.2.1 Driver interviews and surveys

  - 1.2.2.2 Operator workshops

  - 1.2.2.3 City transportation department consultation

- 1.2.3 Software Requirements Specification

  - 1.2.3.1 Use case catalog

  - 1.2.3.2 Non-functional requirements

  - 1.2.3.3 Use case and sequence diagrams

  - 1.2.3.4 Requirements traceability matrix

- 1.2.4 UX and UI design

  - 1.2.4.1 Wireframes

  - 1.2.4.2 High-fidelity mockups

  - 1.2.4.3 Design system and component library

- 1.2.5 System architecture

  - 1.2.5.1 Architecture decision records

  - 1.2.5.2 Data model and entity relationship diagram

  - 1.2.5.3 API contract specification

1.3 Backend and API

- 1.3.1 Environment setup and CI/CD pipeline

- 1.3.2 Account and authentication service

- 1.3.3 Inventory and availability service

  - 1.3.3.1 Live occupancy ingestion

  - 1.3.3.2 Availability calculation engine

  - 1.3.3.3 Reservation ledger

- 1.3.4 Reservation service

  - 1.3.4.1 Hold and confirm logic

  - 1.3.4.2 Extension and cancellation logic

  - 1.3.4.3 Failed-reservation auto-refund handler

- 1.3.5 Pricing service

- 1.3.6 Notification service

- 1.3.7 Reporting and analytics service

1.4 Mobile Application

- 1.4.1 Application shell and navigation

- 1.4.2 Map and search screens

- 1.4.3 Reserve and pay flow

  - 1.4.3.1 Space selection

  - 1.4.3.2 Payment method handling

  - 1.4.3.3 Confirmation and entry pass

- 1.4.4 Reservation history and receipts

- 1.4.5 Push notification handling

- 1.4.6 iOS build and App Store packaging

- 1.4.7 Android build and Play Store packaging

1.5 Web Application

- 1.5.1 Driver web portal

- 1.5.2 Operator dashboard

  - 1.5.2.1 Listing and capacity management

  - 1.5.2.2 Pricing management

  - 1.5.2.3 Live occupancy view

  - 1.5.2.4 Reporting and export

- 1.5.3 Administrative console

- 1.5.4 Finance and payout screens

1.6 Mapping and Location Services

- 1.6.1 Provider selection and contract

- 1.6.2 Geocoding integration

- 1.6.3 Map rendering and garage pins

- 1.6.4 Navigation handoff to garage entrance

1.7 Payment Integration

- 1.7.1 Gateway selection and contract

- 1.7.2 Payment processing

- 1.7.3 Refund processing

- 1.7.4 Operator payout processing

- 1.7.5 PCI DSS compliance review

1.8 Garage Hardware Integration

- 1.8.1 Gate controller adapter layer

- 1.8.2 Occupancy sensor feed integration

- 1.8.3 License plate recognition integration

- 1.8.4 QR entry pass reader integration

- 1.8.5 Hardware failure and fallback handling

1.9 Quality Assurance and Testing

- 1.9.1 Master test plan

- 1.9.2 Functional testing

  - 1.9.2.1 Test case authoring

  - 1.9.2.2 Test execution and defect logging

  - 1.9.2.3 Regression suite automation

- 1.9.3 Integration testing

- 1.9.4 Performance and load testing

- 1.9.5 Security and penetration testing

- 1.9.6 Accessibility testing

- 1.9.7 User acceptance testing support

1.10 Pilot and User Acceptance

- 1.10.1 Pilot garage selection

- 1.10.2 Pilot deployment

- 1.10.3 Operator training materials

- 1.10.4 User acceptance testing and sign-off

1.11 Deployment and Launch

- 1.11.1 Production environment provisioning

- 1.11.2 App store submission and approval

- 1.11.3 Data migration and cutover

- 1.11.4 Public launch

- 1.11.5 Post-launch hypercare support

### 5.3 WBS Dictionary (Level 2)

| ID | Work package | Key deliverable | Owning team |
| --- | --- | --- | --- |
| 1.1 | Project Management | Project plan, status reports, risk register | Project Management Office |
| 1.2 | Requirements and Design | Approved SRS, UI designs, architecture | All teams, led by PMO |
| 1.3 | Backend and API | Deployed API services and data layer | Backend/API Team |
| 1.4 | Mobile Application | iOS and Android apps in the stores | Mobile Application Team |
| 1.5 | Web Application | Driver portal and operator dashboard | Web Application Team |
| 1.6 | Mapping and Location Services | Working map, search, and navigation handoff | Mapping & Location Services Team |
| 1.7 | Payment Integration | PCI-compliant payments, refunds, payouts | Payment Integration Team |
| 1.8 | Garage Hardware Integration | Live gate control and occupancy feed | Backend/API Team with vendor support |
| 1.9 | Quality Assurance and Testing | Test plan, executed suites, defect reports | QA & Testing Team |
| 1.10 | Pilot and User Acceptance | Signed-off pilot at live garages | QA & Testing Team with PMO |
| 1.11 | Deployment and Launch | Platform live in production | All teams |

### 5.4 Decomposition Notes

- Branches 1.3 through 1.8 run partly in parallel, since they are owned by different teams. The dependency that controls the order is the API contract in 1.2.5.3 — no client work starts before it is signed off.

- Branch 1.8 carries the most estimating uncertainty because it depends on third-party gate hardware that varies by garage. It is decomposed further than the others for that reason.

- Branch 1.1 runs for the full duration of the project rather than as a phase, so it appears as a single continuous bar on the schedule in Section 6.

## 6. Draft Project Timeline

### 6.1 Scheduling Approach and Assumptions

The schedule below is a first draft built from the WBS in Section 5. It is constrained by the fixed semester timeline in Section 3.9: the project must be delivered by December 4, 2026. That end date is not negotiable, so the schedule was built backward from it. It will be refined once resource assignments and effort estimates are complete.

Assumptions used:

- A-5: The schedule is bounded by the fixed semester timeline named in Section 3.9. The project starts August 28, 2026 and must deliver by December 4, 2026 — a 14-week schedule.

- A-6: All six delivery teams are available for the full duration and are fully staffed from day one. Budget is not a constraint (Section 3.9), so teams work in parallel wherever dependencies allow.

- A-7: Client sign-off on requirements is time-boxed to one week and is included in the Requirements and Design phase. The compressed schedule leaves no room for a longer review.

- A-8: Third-party contracts for mapping, payments, and gate hardware are signed during the Requirements and Design phase, so integration work is not blocked by procurement.

- A-9: Durations are in calendar weeks and assume a standard five-day work week. The Thanksgiving break, November 23–27, is treated as non-working time and is absorbed inside the Deployment and Launch phase.

- A-10: Because the timeline is fixed and cannot extend, scope is the variable. The out-of-scope list in Section 3.7 is what makes a 14-week delivery possible.

### 6.2 Phase Schedule

| WBS | Phase | Start | Finish | Duration | Depends on |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Management | Aug 28, 2026 | Dec 4, 2026 | 14 wk | — (runs throughout) |
| 1.2 | Requirements and Design | Sep 4, 2026 | Oct 2, 2026 | 4 wk | 1.1.1 |
| 1.3 | Backend and API Development | Oct 2, 2026 | Oct 30, 2026 | 4 wk | 1.2.5 |
| 1.4 | Mobile Application | Oct 9, 2026 | Nov 6, 2026 | 4 wk | 1.2.4, 1.2.5.3 |
| 1.5 | Web Application | Oct 9, 2026 | Nov 6, 2026 | 4 wk | 1.2.4, 1.2.5.3 |
| 1.6 | Mapping and Location Services | Oct 16, 2026 | Oct 30, 2026 | 2 wk | 1.3.1, 1.6.1 |
| 1.7 | Payment Integration | Oct 16, 2026 | Nov 6, 2026 | 3 wk | 1.3.1, 1.7.1 |
| 1.8 | Garage Hardware Integration | Oct 23, 2026 | Nov 6, 2026 | 2 wk | 1.3.3 |
| 1.9 | Quality Assurance and Testing | Oct 30, 2026 | Nov 20, 2026 | 3 wk | 1.3, 1.4, 1.5 (rolling) |
| 1.10 | Pilot and User Acceptance | Nov 6, 2026 | Nov 20, 2026 | 2 wk | 1.9.2, 1.8 |
| 1.11 | Deployment and Launch | Nov 20, 2026 | Dec 4, 2026 | 2 wk | 1.10.4 |

### 6.3 Milestones

| ID | Milestone | Target date | Gate criteria |
| --- | --- | --- | --- |
| M1 | Project kickoff | Aug 28, 2026 | Charter approved and teams assigned |
| M2 | Requirements approved | Oct 2, 2026 | Client sign-off on SRS and API contract |
| M3 | Backend feature complete | Oct 30, 2026 | All API endpoints deployed to staging |
| M4 | Code complete | Nov 6, 2026 | All integrations done, feature freeze |
| M5 | UAT sign-off | Nov 20, 2026 | Pilot garages running with no severity-1 defects |
| M6 | Launch | Dec 4, 2026 | Apps approved in both stores, production live |

### 6.4 Gantt Chart

Figure 1: Draft project schedule for the Smart Parking Platform, August through December 2026. Diamonds mark the six project milestones listed in Section 6.3.

### 6.5 Critical Path

The longest dependent chain through the schedule is:

- 1.1.1 Project charter

- 1.2 Requirements and Design

- 1.3 Backend and API

- 1.9 Quality Assurance and Testing

- 1.10 Pilot and User Acceptance

- 1.11 Deployment and Launch

This chain has no slack. The December 4 delivery date is fixed and cannot move, so any delay in requirements sign-off (M2) has to be absorbed by cutting scope rather than by extending the schedule. Every client-side and integration branch waits on the API contract produced in the Requirements and Design phase.

The compressed timeline changes the risk profile. On a longer schedule a two-week slip is recoverable; here it consumes half a phase.

Three risks sit directly on this path and will be carried into the risk register:

- Requirements sign-off slipping past October 2. The client has three separate stakeholder groups — operators, drivers, and the city transportation department — and their priorities may conflict. Sign-off is time-boxed to one week, which is aggressive.

- Garage hardware integration (1.8) running long. It is not on the critical path today, but it feeds the pilot in 1.10, and it has only two weeks. Any vendor delay makes it critical immediately.

- Testing compressed against the Thanksgiving break. QA ends November 20 and deployment runs through a week with no working days. There is no recovery window between UAT sign-off and delivery.

### 6.6 Effort Estimates by Work Package

Section 6.2 gives each branch a duration in weeks. Duration is not effort: a two-week branch worked by one part-time engineer costs far less than a two-week branch worked by four people. The table below converts the staffing in Section 9.2 into hours and cost per branch, so the schedule and the budget are answering the same question.

| WBS | Branch | Hours | Share | Labor cost |
| --- | --- | --- | --- | --- |
| 1.1 | Project Management | 560 | 8% | $42,000 |
| 1.2 | Requirements and Design | 816 | 11% | $57,680 |
| 1.3 | Backend and API | 1,552 | 21% | $121,120 |
| 1.4 | Mobile Application | 1,008 | 14% | $78,960 |
| 1.5 | Web Application | 1,008 | 14% | $70,000 |
| 1.6 | Mapping and Location Services | 224 | 3% | $15,680 |
| 1.7 | Payment Integration | 552 | 8% | $43,120 |
| 1.8 | Garage Hardware Integration | 384 | 5% | $34,560 |
| 1.9 | Quality Assurance and Testing | 756 | 10% | $44,100 |
| 1.10 | Pilot and User Acceptance | 252 | 3% | $14,700 |
| 1.11 | Deployment and Launch | 224 | 3% | $19,040 |
|  | Total | 7,336 | 100% | $540,960 |

The totals reconcile exactly with Section 9.2, which is the check that matters — the same hours are being counted once.

Three things the effort view shows that the Gantt chart in Section 6.4 does not:

- Backend and API is 21% of the project effort, more than any other branch and nearly twice the next largest. The Gantt chart shows it as a four-week bar like several others, which understates it.

- Mapping, hardware and deployment together are 11% of effort but occupy much of the visual width of the schedule, because they are short branches worked by part-time specialists.

- Quality assurance and the pilot together are 14%, which is low for a platform that commits to a sub-0.5% gate failure rate in BO-2. This is the first place to add people if the contingency in Section 9.3 is released.

### 6.7 Open Scheduling Items

- Resource levelling once team sizes are confirmed, which Section 9.7 also tracks

- A second-pass duration estimate for branches 1.9 and 1.10, where Section 6.6 shows the effort share is low against the quality target in BO-2

Closed in version 1.5: effort estimates per work package are now Section 6.6. Two items are closed as decisions rather than as work. There is no schedule buffer on the critical path — Section 6.5 explains that the December 4 date is fixed, so the buffer is scope, not time, and the money equivalent is the contingency in Section 9.3. The holiday calendar is settled: Thanksgiving, November 23 to 27, is the only non-working period inside the schedule and is absorbed in branch 1.11 under assumption A-9.

## 7. Product Backlog and Sprint 1 Plan

### 7.1 Approach

The requirements in Section 4 describe what the system must do. This section turns them into work the teams can pull from. Every backlog item is written as a user story in the form as a [role], I want [goal], so that [benefit], so that the reason for the work stays attached to the work itself.

Items are estimated in story points on a Fibonacci scale — 1, 2, 3, 5, 8 — rather than in hours. After the split described in Section 7.10, nothing currently sits at 8: the largest story on the board is a 5, which is the size the teams can finish inside one sprint with confidence. Points measure relative size and uncertainty, not time. An 8-point item is not four times a 2-point item in hours; it is an item the team is far less certain about.

Priority uses MoSCoW: Must for items without which the first release does not work, Should for items that matter but could slip a release, Could for items that improve the product but are safe to drop under schedule pressure. Given the fixed December 4 deadline in Section 6, the Could items are the scope buffer.

The backlog is a living list. It will be re-groomed at the start of every sprint, and items will be split as the teams learn more.

### 7.2 Epic Overview

| Epic | Prefix | Items | Points | Covers |
| --- | --- | --- | --- | --- |
| Login and Accounts | LOG | 10 | 30 | Registration, authentication, roles, vehicle profiles |
| User Interface | UI | 21 | 71 | Driver app and web, operator dashboard, admin console |
| Backend Processes | BE | 26 | 116 | Services, availability engine, payments, hardware, integrations |
| Reporting and Analytics | RPT | 12 | 41 | Operator reports, finance statements, driver history |
| Total |  | 69 | 258 |  |

### 7.3 Backlog — Login and Accounts

| ID | User story | Points | Priority |
| --- | --- | --- | --- |
| LOG-01 | As a driver, I want to create an account with my email and password so that I can save my reservations. | 3 | Must |
| LOG-02 | As a driver, I want to verify my email address so that my account is secure. | 2 | Must |
| LOG-03 | As a driver, I want to log in with my credentials so that I can reach my reservations. | 2 | Must |
| LOG-04 | As a driver, I want to reset a forgotten password so that I can get back into my account. | 3 | Must |
| LOG-05 | As a driver, I want to stay signed in on my phone so that I do not log in every trip. | 2 | Should |
| LOG-06 | As a driver, I want to sign up with Google or Apple so that registration is faster. | 5 | Could |
| LOG-07 | As an operator, I want to log in to the operator dashboard so that I can manage my garage. | 3 | Must |
| LOG-08 | As an administrator, I want role-based permissions so that each user only sees what their role allows. | 5 | Must |
| LOG-09 | As a driver, I want to save my vehicle and licence plate so that gate entry works automatically. | 3 | Must |
| LOG-10 | As a driver, I want to sign out of all devices so that I can secure a lost phone. | 2 | Should |

### 7.4 Backlog — User Interface

Covers both sides of the platform. Items UI-01 to UI-16 are the driver experience; UI-17 to UI-21 are the operator dashboard and administrative console.

| ID | User story | Points | Priority |
| --- | --- | --- | --- |
| UI-01 | As a driver, I want to see garages as pins on an interactive map so that I can find parking near me. | 5 | Must |
| UI-02 | As a driver, I want to search by address or landmark so that I can plan parking before I leave. | 3 | Must |
| UI-03 | As a driver, I want to use my current location so that I can find parking without typing. | 2 | Must |
| UI-04 | As a driver, I want to filter by price, walking distance, covered parking and accessible spaces so that results match my needs. | 5 | Should |
| UI-05 | As a driver, I want to sort results by price or distance so that I can compare options quickly. | 2 | Should |
| UI-06 | As a driver, I want a garage detail page with photos, hours, clearance and pricing so that I know what I am booking. | 3 | Must |
| UI-07 | As a driver, I want to pick my arrival and departure time so that I am quoted the right price. | 3 | Must |
| UI-08 | As a driver, I want to see the itemised total before I pay so that there are no surprise fees. | 3 | Must |
| UI-09 | As a driver, I want to reserve and pay in one flow so that booking takes under ninety seconds. | 5 | Must |
| UI-10 | As a driver, I want my QR entry pass in the app so that I can get through the gate. | 3 | Must |
| UI-11 | As a driver, I want turn-by-turn directions to the garage entrance so that I do not circle the building. | 3 | Should |
| UI-12 | As a driver, I want to see upcoming and past reservations so that I can keep track of my parking. | 3 | Must |
| UI-13 | As a driver, I want to download a receipt so that I can claim the expense. | 2 | Should |
| UI-14 | As a driver, I want to extend an active reservation from the app so that I am not rushed back to my car. | 3 | Should |
| UI-15 | As a driver, I want to cancel a reservation and see the refund policy first so that I know what I get back. | 3 | Must |
| UI-16 | As a driver, I want to control which notifications I receive so that I am not spammed. | 2 | Could |
| UI-17 | As an operator, I want a dashboard home showing live occupancy so that I know my garage status at a glance. | 5 | Must |
| UI-18 | As an operator, I want to edit my listing details and photos so that drivers see accurate information. | 3 | Must |
| UI-19 | As an operator, I want to set hourly, daily and event pricing rules so that I can price by demand. | 5 | Must |
| UI-20 | As an operator, I want to see the reservation list for my garage so that I can plan staffing. | 3 | Should |
| UI-21 | As an administrator, I want a console to look up users and resolve disputes so that I can handle support cases. | 5 | Should |

### 7.5 Backlog — Backend Processes

These are the services behind the screens. They are written from the point of view of the person who benefits, not the person who builds them, so the value of each service stays visible. Twelve serve drivers, six serve operators, and two are shared infrastructure.

| ID | User story | Points | Priority |
| --- | --- | --- | --- |
| BE-01 | As a driver, I want my account credentials kept secure so that nobody else can use my account. | 5 | Must |
| BE-02 | As a driver, I want to stay signed in across the app and the website so that I do not log in twice. | 5 | Must |
| BE-03 | As an operator, I want my garages, spaces and capacity held in one place so that every channel shows the same numbers. | 5 | Must |
| BE-04a | As an operator, I want my gate and sensor events delivered to the platform as they happen so that nothing is lost. | 5 | Must |
| BE-04b | As an operator, I want those events turned into a current occupancy count so that the number I see is the number in the garage. | 3 | Must |
| BE-05a | As a driver, I want availability calculated from live occupancy and existing bookings so that a space I reserve really exists. | 5 | Must |
| BE-05b | As a driver, I want garages without a verified feed marked as estimated so that I know when availability is not guaranteed. | 3 | Must |
| BE-06 | As an operator, I want every hold, booking and cancellation recorded so that my records reconcile at the end of the day. | 5 | Must |
| BE-07 | As a driver, I want my space held while I finish paying so that I do not lose it at checkout. | 5 | Must |
| BE-08 | As a driver, I want the system to check for later bookings before extending so that my extension is honoured. | 5 | Should |
| BE-09 | As a driver, I want cancellations refunded by a clear policy so that I know what I get back. | 5 | Must |
| BE-10a | As a driver, I want a reservation that cannot be honoured detected and refunded automatically so that I am not chasing my money. | 5 | Must |
| BE-10b | As a driver, I want a comparable alternate space offered at the same time so that I can still park. | 3 | Must |
| BE-11 | As an operator, I want pricing rules applied automatically by time of day and event so that I do not reprice by hand. | 5 | Must |
| BE-12a | As a driver, I want my card captured as a token and charged through the gateway so that my details never reach our servers. | 5 | Must |
| BE-12b | As an administrator, I want our PCI DSS scope reviewed and evidenced so that we can prove compliance at audit. | 3 | Must |
| BE-13 | As an operator, I want my share of revenue calculated each period so that I am paid accurately and on time. | 5 | Should |
| BE-14 | As a driver, I want alerts delivered by push, email or SMS so that I receive them on whatever I am using. | 5 | Must |
| BE-15a | As an operator, I want the platform to drive my gate through a common adapter so that one integration covers my hardware. | 5 | Must |
| BE-15b | As an operator, I want a second vendor supported and conformance-tested so that the adapter is proven on more than one rig. | 3 | Must |
| BE-16a | As a driver, I want my plate read and matched to my reservation so that the gate opens without me doing anything. | 5 | Must |
| BE-16b | As a driver, I want a low-confidence plate read handled gracefully so that a bad read does not leave me stuck. | 3 | Must |
| BE-17 | As a driver, I want a QR pass as a backup so that a failed plate read does not strand me at the gate. | 5 | Must |
| BE-18 | As a driver, I want addresses and routes resolved accurately so that search and navigation take me to the right entrance. | 5 | Must |
| BE-19 | As an administrator, I want an unchangeable log of financial and admin actions so that disputes can be investigated. | 3 | Should |
| BE-20 | As a developer, I want deployment pipelines and separate environments so that the team can release safely from day one. | 5 | Must |

### 7.6 Backlog — Reporting and Analytics

Reporting serves three audiences: operators who need to understand their garages, finance users who need to reconcile payouts, and drivers who need their own parking history.

| ID | User story | Points | Priority |
| --- | --- | --- | --- |
| RPT-01 | As an operator, I want a live occupancy widget so that I can see spaces used right now. | 3 | Must |
| RPT-02 | As an operator, I want a daily revenue summary so that I can track takings without a spreadsheet. | 3 | Must |
| RPT-03 | As an operator, I want a utilization rate report for any date range so that I can see how well the garage is used. | 5 | Must |
| RPT-04 | As an operator, I want a peak hours report so that I can set pricing around demand. | 3 | Should |
| RPT-05 | As an operator, I want average parking duration so that I can plan capacity. | 3 | Should |
| RPT-06 | As an operator, I want a reserved versus walk-in split so that I can see what the platform is bringing in. | 3 | Should |
| RPT-07 | As an operator, I want to export any report to CSV or PDF so that I can share it with my finance team. | 3 | Must |
| RPT-08 | As a finance user, I want a payout statement per operator per period so that payouts can be reconciled. | 5 | Must |
| RPT-09 | As a finance user, I want a refund and dispute report so that I can spot patterns of failed reservations. | 3 | Should |
| RPT-10 | As an administrator, I want a failed gate entry incident report so that hardware problems are caught early. | 5 | Should |
| RPT-11 | As a driver, I want a summary of my parking history so that I can see where and how often I park. | 2 | Could |
| RPT-12 | As a driver, I want an annual expense export so that I can claim parking on my taxes. | 3 | Could |

### 7.7 Sprint 1 Plan

Sprint 1 dates: October 2 to October 16, 2026 (two weeks)
Sprint goal: A driver can create an account, log in, and see real garages with live availability on a map.

Sprint 1 deliberately builds the spine of the product rather than the most visible features. Nothing else in the backlog can be built or demonstrated until accounts, sessions, the inventory service and the deployment pipeline exist. The map is included so the sprint ends with something a stakeholder can actually look at, which is the point of a sprint review.

| ID | User story | Points |
| --- | --- | --- |
| LOG-01 | As a driver, I want to create an account with my email and password so that I can save my reservations. | 3 |
| LOG-02 | As a driver, I want to verify my email address so that my account is secure. | 2 |
| LOG-03 | As a driver, I want to log in with my credentials so that I can reach my reservations. | 2 |
| LOG-04 | As a driver, I want to reset a forgotten password so that I can get back into my account. | 3 |
| UI-01 | As a driver, I want to see garages as pins on an interactive map so that I can find parking near me. | 5 |
| UI-02 | As a driver, I want to search by address or landmark so that I can plan parking before I leave. | 3 |
| UI-03 | As a driver, I want to use my current location so that I can find parking without typing. | 2 |
| BE-01 | As a driver, I want my account credentials kept secure so that nobody else can use my account. | 5 |
| BE-02 | As a driver, I want to stay signed in across the app and the website so that I do not log in twice. | 5 |
| BE-03 | As an operator, I want my garages, spaces and capacity held in one place so that every channel shows the same numbers. | 5 |
| BE-20 | As a developer, I want deployment pipelines and separate environments so that the team can release safely from day one. | 5 |
|  | Sprint 1 total | 40 |

Why these items

- BE-20 comes first. Without pipelines and environments, nothing else can be deployed or tested.

- BE-01, BE-02, LOG-01 to LOG-04 are the account spine. Every other story assumes a logged-in user.

- BE-03 establishes garages and spaces as data. The map has nothing to draw without it.

- UI-01 to UI-03 give the sprint a visible outcome and prove the backend works end to end.

Deferred on purpose

Payments (BE-12), reservations (BE-07) and gate hardware (BE-15, BE-16) are all Must items but none belongs in Sprint 1. Each depends on the inventory and account services being stable first, and taking them early would mean building on foundations that are still moving.

Definition of done for Sprint 1

An item is done when the code is merged, unit tests pass, it is deployed to the staging environment, and it has been demonstrated against the sprint goal at the review.

### 7.8 Acceptance Criteria — Sprint 1

A story is not ready to pull until someone can say what “done” means for it. The eleven stories committed to Sprint 1 are written out below. Stories in later sprints get their criteria at the grooming session before that sprint, not now, because writing them earlier means rewriting them.

| Story | Acceptance criteria |
| --- | --- |
| BE-20 | Pipelines build and deploy to dev, staging and production; a failing test blocks the deploy; a rollback restores the previous build. |
| BE-01 | Passwords are stored salted and hashed; no plaintext password appears in logs or the database; a password reset invalidates the old one. |
| BE-02 | A session token is issued on login, expires after the configured period, and is rejected after sign-out; the same token works on web and mobile. |
| BE-03 | A garage can be created with its spaces and capacity; capacity cannot be set below the number of confirmed reservations; the record is the only source the map reads. |
| LOG-01 | A new account is created from email, password and name; a duplicate email is refused with a clear message; the account is inactive until verified. |
| LOG-02 | A verification email arrives within two minutes; the link activates the account once and then expires; an expired link offers to resend. |
| LOG-03 | Correct credentials open a session; wrong credentials are refused without saying which field was wrong; three failures lock the account temporarily. |
| LOG-04 | A reset link is emailed, works once, and expires after one hour; setting a new password ends all other sessions. |
| UI-01 | Garage pins render on the map within 2 seconds for 95% of searches (NFR-1); each pin shows price and live space count; the count refreshes as gate events arrive. |
| UI-02 | An address or landmark returns garages ordered by distance; an unrecognised address returns a clear message, not an empty map. |
| UI-03 | With location permission granted the map centres on the driver; with it denied the app asks for an address instead of failing. |

These sit alongside the sprint definition of done in Section 7.7, which applies to every story. A story meets its own criteria and the definition of done before it moves.

### 7.9 Product Backlog Board

The backlog is maintained as a Trello board so that the teams can move work through the sprint rather than read it from a document. The board below was refreshed for version 1.5 and shows the twelve split stories in place of the six 8-point originals. The four epic lists hold the remaining backlog and the Sprint 1 list holds the committed work for the current sprint. Card titles carry the story ID, the estimate and the MoSCoW priority, so the board and Section 7.3 to 7.6 stay in step.

Figure 2: Product backlog board in Trello. The four epic lists hold the remaining 58 stories; the Sprint 1 list holds the 11 stories committed for the sprint beginning October 2, 2026.

As sprints progress, the board will gain the usual working columns — In Progress, In Review and Done — so that flow can be tracked. They are left off for now because Sprint 1 has not started.

### 7.10 Open Backlog Items

- Sprint 2 and Sprint 3 planning, once Sprint 1 reports a real velocity

- Acceptance criteria for stories beyond Sprint 1, written at each grooming session

Closed in version 1.5: the six 8-point stories are split into twelve sprint-sized stories in Section 7.5, Sprint 1 acceptance criteria are in Section 7.8, and every story now traces to a use case in Section 4.7.

## 8. Risk Management and Communication Plan

### 8.1 Risk Management Approach

Risks were identified by walking the WBS in Section 5 branch by branch, the schedule in Section 6, and the assumptions in Sections 3.9 and 6.1. Every assumption is a risk in disguise: if it turns out to be false, something breaks.

Each risk is scored on two scales:

- Probability — Low (1), Medium (2), High (3): how likely it is to happen.

- Impact — Low (1), Medium (2), High (3): what it costs us if it does.

The risk score is probability multiplied by impact, so it runs from 1 to 9. Anything scoring 6 or higher gets an owner and an active response now. Anything scoring 3 or 4 is monitored. Anything at 1 or 2 is logged and reviewed monthly.

Four response strategies are used:

| Strategy | What it means | When we use it |
| --- | --- | --- |
| Avoid | Change the plan so the risk cannot happen | The risk would sink the project and the plan can be changed |
| Mitigate | Reduce the probability or the impact | Most risks land here |
| Transfer | Move the consequence to a third party | Insurance, vendor contracts, SLAs |
| Accept | Do nothing in advance; handle it if it happens | Cost of the response exceeds the cost of the risk |

Because the December 4 deadline in Section 6 is fixed and cannot move, schedule risks carry more weight on this project than they would normally. When a schedule risk materialises here, the only lever available is scope.

### 8.2 Risk Identification by Category

Technical risks

| ID | Risk |
| --- | --- |
| T-1 | Live occupancy feeds from garage sensors are less accurate than the 30-second target in NFR-2, so availability shown to drivers is wrong |
| T-2 | Gate hardware differs by vendor and the adapter layer in WBS 1.8.1 does not cover every garage in the pilot |
| T-3 | Licence plate recognition misreads plates in rain, at night, or on damaged plates, so drivers are stuck at the gate |
| T-4 | Payment integration pulls more of the system into PCI DSS scope than expected, forcing rework in the backend |
| T-5 | The availability engine has a race condition under load and sells the same space twice, breaking the core promise of the product |

Schedule risks

| ID | Risk |
| --- | --- |
| S-1 | Requirements sign-off slips past October 2 because three stakeholder groups cannot agree, delaying every downstream branch |
| S-2 | Garage hardware integration has only two weeks in the schedule and any vendor delay pushes it onto the critical path |
| S-3 | The Thanksgiving break, November 23 to 27, removes the only recovery window between UAT sign-off and delivery |
| S-4 | App store review takes longer than the three weeks allowed in WBS 1.11.2 and the public launch misses December 4 |
| S-5 | Mobile, web and integration teams sit idle waiting on the API contract from WBS 1.2.5.3 |

Financial risks

| ID | Risk |
| --- | --- |
| F-1 | Payment gateway per-transaction fees are higher than modelled, cutting the margin on every reservation |
| F-2 | Mapping and geocoding API costs scale with usage and become the largest running cost at launch volume |
| F-3 | Automatic refunds under NFR-11 create a liability we cannot forecast until occupancy feeds are proven |
| F-4 | Pilot garages need sensor or camera retrofits that were not in the hardware budget |
| F-5 | Errors in operator payout calculation create reconciliation work and damage trust with the paying client |

People risks

| ID | Risk |
| --- | --- |
| P-1 | A specialist on payments or licence plate recognition becomes unavailable and no one else can pick the work up |
| P-2 | Six teams working in parallel create coordination overhead that slows everyone down |
| P-3 | Operator stakeholders are slow to respond to questions, blocking requirements and pilot scheduling |
| P-4 | Drivers, operators and the city transportation department want different things, and no one has final say |
| P-5 | Knowledge of the availability engine sits with one person, so any absence stops the critical path |

### 8.3 Risk Register

In the table below, P is probability and I is impact, each rated Low, Med or High. Score is the two multiplied, as described in Section 8.1. The twelve risks below scored 3 or higher and are actively managed. The remaining eight are logged as watch items and reviewed at the monthly steering meeting.

| ID | Risk | P | I | Score | Owner | Response | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-1 | Requirements sign-off slips past October 2 | High | High | 9 | Project Manager | Mitigate — time-box review to one week, get written sign-off criteria agreed up front, escalate to steering on day 3 | Open |
| S-2 | Garage hardware integration runs past its two weeks | High | Med | 6 | Backend Lead | Mitigate — start vendor technical calls during requirements, build the adapter against two vendors first | Open |
| T-3 | Plate recognition fails in poor conditions | High | Med | 6 | Backend Lead | Mitigate — QR pass fallback in WBS 1.8.4 plus an in-app support code; target 95% read rate, not 100% | Open |
| P-4 | Stakeholder groups want different things | High | Med | 6 | Project Manager | Mitigate — name a single product owner on the client side with final say before requirements start | Open |
| T-1 | Occupancy feeds less accurate than NFR-2 requires | Med | High | 6 | Backend Lead | Mitigate — mark garages without a verified feed as “availability estimated” and block guaranteed booking there | Open |
| T-5 | Availability engine double-books a space | Med | High | 6 | Backend Lead | Mitigate — pessimistic locking on the reservation ledger, load test before the pilot; auto-refund in NFR-11 as backstop | Open |
| S-4 | App store review delays the December 4 launch | Med | High | 6 | Mobile Lead | Mitigate — submit a review build four weeks early during UAT; prepare the web app as the launch path if stores slip | Open |
| T-2 | Adapter layer misses a pilot garage’s hardware | Med | Med | 4 | Backend Lead | Mitigate — survey hardware at all pilot garages before WBS 1.8 starts; choose pilot sites by hardware match | Open |
| F-1 | Gateway fees higher than modelled | Med | Med | 4 | Finance Lead | Transfer — fix the rate in the gateway contract signed during WBS 1.7.1 | Open |
| F-3 | Refund liability under NFR-11 is unforecastable | Med | Med | 4 | Finance Lead | Accept and monitor — track refund rate weekly from the pilot; revisit if it exceeds 1% of reservations | Open |
| S-3 | Thanksgiving break removes the recovery window | High | Low | 3 | Project Manager | Avoid — move the deployment buffer earlier so no critical work sits in that week | Open |
| P-1 | A payments or LPR specialist becomes unavailable | Low | High | 3 | Project Manager | Mitigate — pair every specialist area with a second engineer from week one | Open |

Watch list (reviewed monthly, not actively managed): T-4, S-5, F-2, F-4, F-5, P-2, P-3, P-5.

### 8.4 Probability and Impact Matrix

Figure 3: Probability and impact matrix for the twelve actively managed risks. Red and orange cells require an active response; yellow cells are monitored; green cells are accepted.

The matrix makes the shape of the project clear. The top-right cluster is almost entirely schedule and integration risk, which follows directly from the fixed deadline in Section 6. There is nothing in the low-probability, low-impact corner worth tracking, because those risks were filtered out during identification.

### 8.5 Risk Triggers

A risk register with no triggers is a list of worries. A trigger is the specific, observable thing that tells us a risk has stopped being hypothetical, so that the response in Section 8.3 starts on evidence rather than on a feeling. Each of the twelve actively managed risks has one.

| Risk | Trigger — the signal that it is becoming an issue | Watched by | Checked |
| --- | --- | --- | --- |
| S-1 | No named client product owner by September 18, or a second round of conflicting written comments on the SRS | Project Manager | Weekly |
| S-2 | Any pilot garage vendor has not returned hardware specifications by October 9 | Backend Lead | Weekly |
| T-3 | Plate read rate below 95% on any day of bench testing | Backend Lead | Daily in test |
| P-4 | Two stakeholder groups give opposing answers to the same requirement question | Project Manager | Per elicitation session |
| T-1 | Occupancy feed lag exceeds the 30-second NFR-2 target in more than 1% of samples | Backend Lead | Daily in test |
| T-5 | Any double-booking observed in load testing, at any volume | Backend Lead | Per load test |
| S-4 | App store review build not submitted by November 6, or a first submission rejected | Mobile Lead | Weekly from Nov 1 |
| T-2 | A hardware survey finds a vendor not covered by the adapter interface | Backend Lead | Once, before 1.8 starts |
| F-1 | Quoted gateway rate in the signed contract exceeds the modelled rate | Finance Lead | At contract signature |
| F-3 | Refund rate exceeds 1% of reservations in any pilot week | Finance Lead | Weekly from pilot |
| S-3 | Any task on the critical path is still open on November 20 | Project Manager | Daily from Nov 16 |
| P-1 | A specialist area still has only one engineer who can work in it by October 9 | Project Manager | Every two weeks |

Triggers are deliberately written as thresholds with dates or numbers in them. “Requirements are going badly” is not a trigger; “no named product owner by September 18” is.

### 8.6 Expected Monetary Value — Financial Risks

The five financial risks in Section 8.2 are the ones that can be costed, so they are the ones worth quantifying. Probability bands are converted to a single figure at the midpoint of each band: Low 20%, Med 50%, High 80%. Impact is the cost to the project if the risk occurs.

| Risk | Description | Probability | Impact | EMV |
| --- | --- | --- | --- | --- |
| F-1 | Gateway fees higher than modelled | Med (50%) | $18,000 | $9,000 |
| F-2 | Mapping and geocoding API costs scale with usage | Med (50%) | $12,000 | $6,000 |
| F-3 | Refund liability under NFR-11 cannot be forecast | Med (50%) | $25,000 | $12,500 |
| F-4 | Pilot garages need unbudgeted sensor or camera retrofits | Low (20%) | $20,000 | $4,000 |
| F-5 | Operator payout calculation errors create rework | Low (20%) | $15,000 | $3,000 |
|  | Total expected monetary value |  |  | $34,500 |

What this tells us about the contingency. The contingency reserve in Section 9.3 is $119,175. The expected monetary value of the financial risks is $34,500, which is 29% of it. The remaining $84,675 is what absorbs the schedule and technical risks, which cannot be costed this cleanly but are scored higher: six of the seven risks at score 6 or above are technical or schedule, not financial.

So the 15% contingency is defensible, but it is not generous. If the expected monetary value rises above roughly half the reserve, the response is to cut scope from the Could items in Section 7, not to ask for more money — Section 3.9 fixes the timeline, and scope is the only variable the project actually controls.

### 8.7 Communication Plan

Meeting cadence

| Meeting | Who attends | How often | Length | Purpose |
| --- | --- | --- | --- | --- |
| Team stand-up | Each delivery team separately | Daily, 9:15am | 15 min | What was done, what is next, what is blocked |
| Scrum of scrums | One lead from each of the six teams | Twice weekly, Tue and Thu | 30 min | Cross-team blockers and dependencies |
| Sprint planning | Delivery team plus product owner | Every two weeks, sprint start | 2 hr | Commit to the sprint backlog |
| Sprint review | Delivery teams, product owner, client | Every two weeks, sprint end | 1 hr | Demonstrate working software |
| Sprint retrospective | Each delivery team | Every two weeks, sprint end | 45 min | What to change in how we work |
| Stakeholder update | Project Manager to all stakeholders | Weekly, Thursday | Async video | What changed this week, what is next |
| Risk review | Project Manager and team leads | Every two weeks | 45 min | Re-score the register, close and open risks |
| Steering committee | Client sponsors, PM, delivery leads | Monthly | 1 hr | Budget, scope changes, escalated decisions |

Reporting methods

| Report | Audience | Format | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Sprint burndown | Delivery teams | Trello board, live | Continuous | Team leads |
| Weekly status update | All stakeholders | 1–2 minute recorded video | Weekly | Project Manager |
| Project document | All stakeholders | This document, versioned in GitHub | Weekly | Project Manager |
| Risk register | Steering committee, team leads | Section 8.3 of this document | Every two weeks | Project Manager |
| Occupancy and revenue reports | Operators, finance | Platform reports in WBS 1.5.2.4 | Daily and monthly | Operator dashboard |
| Defect report | QA, delivery leads | Test management tool | Daily during test phases | QA Lead |
| Milestone report | Client sponsors | One-page summary at each milestone | Six times (M1–M6) | Project Manager |

Escalation path

- Raised in the team stand-up and handled by the team lead.

- Unresolved after one working day, raised at the scrum of scrums.

- Unresolved after three working days, or affecting the critical path, escalated to the Project Manager.

- Affecting scope, budget, or the December 4 delivery date, escalated to the steering committee within 24 hours.

Anything on the critical path in Section 6.5 skips straight to step 3. There is no slack to absorb a slow escalation.

Communication principles

- Written first. Decisions made in a meeting are recorded in this document or on the board within 24 hours.

- One source of truth. The project document in the public repository is the current state; anything else is a draft.

- Bad news early. A risk raised late costs more than a risk raised wrong.

### 8.8 Stakeholder Communication Matrix

Section 3.8 lists who the stakeholders are and Section 8.7 lists the meetings. This matrix joins them: for each stakeholder, how much they care, how much say they have, and through which channel they actually hear from us.

| Stakeholder | Interest | Influence | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- | --- |
| Drivers / vehicle owners | High | Low | In-app release notes and notifications | Per release | Product Owner |
| Parking facility operators | High | High | Sprint review plus operator dashboard | Every two weeks | Project Manager |
| City transportation department | Medium | Medium | Milestone summary report | At each milestone | Project Manager |
| System administrators | Medium | Medium | Runbook and release notes | Per release | DevOps Engineer |
| Finance and billing personnel | High | Medium | Payout statement and refund report | Monthly | Finance Analyst |
| Mobile application users | High | Low | App store release notes | Per release | Mobile Lead |
| Third-party payment providers | Medium | Medium | Integration status call | Monthly | Payment Integration Engineer |
| $oftware ¢orp. delivery teams | High | High | Stand-up and scrum of scrums | Daily / twice weekly | Team leads |

The matrix is what stops the communication plan from being generic. High interest with high influence — operators and the delivery teams — gets a two-way channel on a short cycle. High interest with low influence — drivers — gets told, reliably, but is not consulted on every decision. Nobody is on a channel that does not match the say they have.

### 8.9 Open Risk Management Items

- Expected monetary value for the technical and schedule risks, which needs an agreed cost of delay from the client before it can be calculated

- A second-pass re-scoring of the whole register after Sprint 1, when the first real velocity and defect data exist

Closed in version 1.5: risk triggers are Section 8.5, expected monetary value for the financial risks is Section 8.6, the stakeholder communication matrix is Section 8.8, and the contingency reserve is sized in Section 9.3.

## 9. Resource and Cost Plan

### 9.1 Approach

Section 3.9 records an unlimited theoretical development budget as constraint C-1. That removes cost as a limit, but it does not remove the need for a cost plan. The client still has to know what the platform costs to build, finance has to forecast cash month by month, the financial risks F-1 to F-5 in Section 8.2 need a baseline to be measured against, and earned value cannot be calculated without a budget at completion. This section therefore produces a full costing and treats the result as the performance baseline rather than as a spending cap.

The estimate is built bottom-up. Every role in Section 9.2 is costed from hours multiplied by rate, every non-labor item in Section 9.3 is a separately identified purchase, and the two are summed. Bottom-up was chosen over top-down because the Work Breakdown Structure in Section 5 is already decomposed to work-package level, which is exactly the input a bottom-up estimate needs. A top-down percentage split would have been faster but would hide which branch of the WBS the money is going to.

Costing assumptions:

- A-11: The schedule is the 14 weeks in Section 6.2, from August 28 to December 4, 2026. One full-time equivalent is 40 hours per week, so 100% allocation equals 560 hours.

- A-12: Rates are blended contractor rates in US dollars and already include recruitment and tooling for the individual. They do not include payroll overhead, which is carried separately.

- A-13: Overhead and benefits are charged at 25% of labor, following standard enterprise practice.

- A-14: Contingency is 15%, at the upper end of the usual 5–20% band. The justification is Section 8.3: seven risks score 6 or higher and the December 4 delivery date cannot move, so the project has no schedule float to absorb problems and must absorb them with money or scope instead.

- A-15: Costs are build costs through launch. Running costs after December 4 are operating expenditure and sit outside this baseline.

### 9.2 Roles and Resources

Eighteen people across the six delivery teams named in Section 3.1, plus the project management office. Names are fictional. Skill level sets the rate; the allocation percentage reflects how much of the 14 weeks each person is needed for, taken from the phase durations in Section 6.2 — the mapping, payments and hardware integration specialists are part-time because their branches run for two to three weeks each, not the full project.

| Role | Name | Skill level | FTE | Hrs | Rate | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | Alice Nguyen | Senior | 100% | 560 | $75 | $42,000 |
| Business Analyst | Marcus Webb | Mid | 60% | 336 | $55 | $18,480 |
| Solution Architect | Priya Raghavan | Principal | 50% | 280 | $105 | $29,400 |
| UX Designer | Sofia Marchetti | Senior | 50% | 280 | $65 | $18,200 |
| Backend Lead | Daniel Osei | Senior | 100% | 560 | $90 | $50,400 |
| Backend Engineer I | Yuki Tanaka | Mid | 100% | 560 | $70 | $39,200 |
| Backend Engineer II | Tomas Herrera | Mid | 100% | 560 | $70 | $39,200 |
| Mobile Lead | Aisha Rahman | Senior | 100% | 560 | $85 | $47,600 |
| Mobile Engineer | Liam Doyle | Mid | 80% | 448 | $70 | $31,360 |
| Web Lead | Elena Petrova | Senior | 100% | 560 | $85 | $47,600 |
| Web Engineer | Noah Brantley | Junior | 80% | 448 | $50 | $22,400 |
| Mapping Integration Engineer | Carlos Mendes | Mid | 40% | 224 | $70 | $15,680 |
| Payment Integration Engineer | Hannah Kirsch | Senior | 50% | 280 | $90 | $25,200 |
| Hardware Integration Engineer | Viktor Novak | Senior | 40% | 224 | $90 | $20,160 |
| QA Lead | Grace Okonkwo | Senior | 100% | 560 | $65 | $36,400 |
| QA Engineer | Ravi Shankar | Mid | 80% | 448 | $50 | $22,400 |
| DevOps Engineer | Jonas Lind | Senior | 60% | 336 | $85 | $28,560 |
| Finance Analyst | Beatriz Lima | Mid | 20% | 112 | $60 | $6,720 |
| Total | 18 people |  | 13.10 FTE | 7,336 |  | $540,960 |

Two allocation notes worth flagging:

- The Backend Lead and both backend engineers are at 100% for the whole project. Branch 1.3 is on the critical path in Section 6.5 and feeds every other team through the API contract, so it is staffed first and never shared.

- The Finance Analyst at 20% is the smallest allocation on the project but is not optional. Operator payouts in WBS 1.7.4 and risk F-5 both need someone who owns reconciliation.

### 9.3 Cost Plan — Bottom-Up

| Item | Category | Qty / Months | Unit cost | Dur. | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Project team labor | Labor | 7,336 hours | blended, see 9.2 | 14 wk | $540,960 | 18 people, 13.10 FTE |
| Cloud hosting (dev, staging, production) | Infrastructure | 4 months | $4,000/month | 4 | $16,000 | Three environments from WBS 1.3.1 |
| Developer tooling and licences | Licences & Tools | 18 seats | $135/seat/month | 4 | $9,600 | IDEs, repo, CI, design tools |
| Mapping and geocoding API usage | Third-party APIs | 4 months | $2,500/month | 4 | $10,000 | Build and test volume, not launch volume |
| Payment gateway integration and certification | Third-party APIs | one-off | $6,000 | n/a | $6,000 | Sandbox plus certification fee |
| Garage sensors and LPR cameras | Hardware | 3 garages | $4,000/garage | n/a | $12,000 | Pilot sites only, WBS 1.8 |
| Mobile test device matrix | Hardware | 10 devices | $800/device | n/a | $8,000 | iOS and Android, NFR-10 |
| Security assessment and PCI DSS audit | Legal & Compliance | one-off | $35,000 | n/a | $35,000 | Required by NFR-6, WBS 1.7.5 |
| Accessibility audit | Legal & Compliance | one-off | $7,500 | n/a | $7,500 | WCAG 2.2 AA, NFR-9 |
| Legal and vendor contract review | Legal & Compliance | one-off | $9,000 | n/a | $9,000 | Gateway, mapping and hardware SLAs |
| App store developer accounts | Licences & Tools | 2 stores | $100/store/yr | n/a | $200 | Apple and Google |
| Operator training materials and delivery | Training | one-off | $5,000 | n/a | $5,000 | WBS 1.10.3 |
| Overhead and benefits | Overhead | 25% | of labor | n/a | $135,240 | Payroll tax, benefits, facilities |
| Subtotal before contingency |  |  |  |  | $794,500 |  |
| Contingency reserve | Reserve | 15% | of subtotal | n/a | $119,175 | Sized against Section 8.3 |
| Grand total |  |  |  |  | $913,675 |  |

The shape of this budget is normal for a software project: labor plus its overhead is 74% of the grand total, and everything else — hardware, licences, audits, APIs — is the remaining 26%. The single largest non-labor line is the security and PCI DSS audit at $35,000, which is not discretionary: NFR-6 requires it before the platform can process a payment.

Three costs here are the “hidden” kind that first-pass estimates usually miss. The mapping and geocoding API charge is metered per request, so it is budgeted at build-and-test volume only; at launch volume it becomes an operating cost and risk F-2 tracks it. The accessibility audit exists solely because NFR-9 commits to WCAG 2.2 Level AA. The garage sensors and cameras are capital spend on someone else’s property, which is why risk F-4 flags it separately.

### 9.4 Budgeted Cashflow

The 14 weeks are split into four budget periods of four, four, four and two weeks. Labor is spread across them according to the phase loading in Section 6.2 rather than evenly: the first period carries only requirements and design, the middle two carry all six teams building in parallel, and the last covers the pilot and launch.

| Period | Labor | Overhead | Non-labor | Contingency | Monthly total | Cumulative |
| --- | --- | --- | --- | --- | --- | --- |
| M1 Aug 28 - Sep 25 | $81,144 | $20,286 | $17,950 | $17,907 | $137,287 | $137,287 |
| M2 Sep 28 - Oct 23 | $173,107 | $43,277 | $22,950 | $35,900 | $275,234 | $412,521 |
| M3 Oct 26 - Nov 20 | $205,565 | $51,391 | $55,950 | $46,936 | $359,842 | $772,363 |
| M4 Nov 23 - Dec 4 | $81,144 | $20,286 | $21,450 | $18,432 | $141,312 | $913,675 |
| Total | $540,960 | $135,240 | $118,300 | $119,175 | $913,675 |  |

Figure 4: Budgeted monthly cashflow for the Smart Parking Platform. Bars show spend by category per period; the line shows cumulative spend against the $913,675 budget at completion.

The colors in Figure 4 are identified in the key below rather than in a legend on the chart itself, so the bars stay readable at page size.

| Key | Category | What it covers | Amount | Share |
| --- | --- | --- | --- | --- |
|  | Labor | Salaries for the 18 people in Section 9.2 | $540,960 | 59% |
|  | Overhead and benefits | Payroll tax, benefits and facilities at 25% of labor | $135,240 | 15% |
|  | Non-labor | Cloud, licences, APIs, hardware, audits and training | $118,300 | 13% |
|  | Contingency | Reserve at 15%, sized against the risk register | $119,175 | 13% |
|  | Total |  | $913,675 | 100% |

Peak spend is $359,842 in period M3. Two things land in that period at once — every delivery team is at full load, and the two largest one-off purchases, the pilot hardware and the security audit, both fall due. Finance should expect roughly 40% of the total project spend inside those four weeks.

The cumulative line is the budget at completion of $913,675, which becomes the planned value curve for earned value tracking. Once Sprint 1 reports actual cost, schedule performance index and cost performance index can be calculated against it at each of the six milestones in Section 6.3.

### 9.5 RACI Matrix

Responsibility is assigned against the Work Breakdown Structure branches in Section 5, so the matrix and the plan use the same vocabulary. R does the work, A is answerable and approves the deliverable, C is consulted before the decision, I is kept informed after it. Every row has exactly one A. Where one group both owns and performs the work, the cell reads A R.

Columns are roles, not individuals: PM Project Manager, PO Product Owner (client side), BA Business Analyst, ARC Solution Architect, UX UX Designer, BE Backend and Integration team, CLI Client teams (mobile and web), QA QA and Testing team, OPS DevOps.

| WBS | Deliverable | PM | PO | BA | ARC | UX | BE | CLI | QA | OPS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Project plan and status reporting | A | C | R | I | I | I | I | I | I |
| 1.2.2 | Requirements elicitation | C | A | R | C | C | C | C | I | I |
| 1.2.3 | Software Requirements Specification | C | A | R | C | C | C | C | C | I |
| 1.2.4 | UX and UI design | I | A | C | C | R | I | C | I | I |
| 1.2.5 | Architecture and API contract | I | C | C | A | I | R | C | I | C |
| 1.3 | Backend and API development | C | C | I | A | I | R | C | C | C |
| 1.4 | Mobile application | A | C | I | C | C | I | R | C | I |
| 1.5 | Web application and operator dashboard | A | C | I | C | C | I | R | C | I |
| 1.6 | Mapping and location services | I | I | I | A | C | R | C | I | C |
| 1.7 | Payment integration | A | C | I | C | I | R | C | C | C |
| 1.8 | Garage hardware integration | A | C | I | C | I | R | I | C | C |
| 1.9 | Quality assurance and testing | C | I | I | I | I | C | C | A R | C |
| 1.10 | Pilot and user acceptance | R | A | I | I | I | C | C | R | C |
| 1.11 | Deployment and launch | A | C | I | C | I | C | R | C | R |
| 7 | Backlog grooming and sprint planning | C | A | R | C | C | C | C | C | I |
| 8.3 | Risk register maintenance | A R | C | C | C | I | C | C | C | C |

Three decisions in this matrix are deliberate and worth stating:

- The Product Owner is accountable for everything that defines the product — requirements, the SRS, the designs, the backlog, and acceptance of the pilot. This is the direct mitigation for risk P-4 in Section 8.3, where three stakeholder groups wanting different things scored 6. A single accountable product owner on the client side is what removes that ambiguity.

- The Solution Architect, not the Project Manager, is accountable for the API contract and the backend. Branch 1.2.5.3 blocks every other team, so the person who owns it has to be the person who understands the technical consequences of changing it.

- QA is accountable for testing, not the delivery teams. A team that tests its own work and signs off on it has no independent check, and NFR-11 commits us to a defect rate the client will measure.

### 9.6 Earned Value Baseline

The cumulative curve in Section 9.4 is the project’s planned value. Reading it at each of the six milestone dates in Section 6.3 gives the baseline that earned value reporting measures against. Budget at completion is $913,675.

| Milestone | Gate | Date | Planned value (PV) | % of BAC |
| --- | --- | --- | --- | --- |
| M1 | Project kickoff | Aug 28, 2026 | $0 | 0% |
| M2 | Requirements approved | Oct 2, 2026 | $181,324 | 20% |
| M3 | Backend feature complete | Oct 30, 2026 | $470,096 | 51% |
| M4 | Code complete | Nov 6, 2026 | $570,851 | 62% |
| M5 | UAT sign-off | Nov 20, 2026 | $772,363 | 85% |
| M6 | Launch | Dec 4, 2026 | $913,675 | 100% |

Once Sprint 1 reports its first actual cost, three numbers get published at every milestone in the status report defined in Section 8.7:

- SPI = EV / PV. Below 1 means behind schedule. Because the December 4 date in Section 6 cannot move, an SPI below 1 is a scope conversation, not a schedule conversation.

- CPI = EV / AC. Below 1 means over budget. The contingency in Section 9.3 covers a CPI down to roughly 0.87 before the reserve is exhausted.

- EAC = BAC / CPI. The forecast final cost at the current rate of spend.

The baseline itself is now fixed. What is still outstanding is actuals, which cannot exist until the first sprint closes.

### 9.7 Open Resource and Cost Items

- Actual cost and earned value figures, which cannot exist until Sprint 1 closes — the baseline itself is set in Section 9.6

- Resource levelling across the two four-week peaks, where several specialists are needed at the same time

- A make-or-buy decision on garage hardware, which may convert capital spend into a vendor subscription

Out of scope for this baseline rather than open: the operating cost forecast for the first year after launch, which is operating expenditure under assumption A-15.

## 10. Next Steps

- Add effort estimates in hours to each work package in Section 5, then resource-level the schedule.

- Start the risk register, beginning with the three critical-path risks named in Section 6.5 and the third-party dependency risks in Section 3.9.

- Run stakeholder analysis and requirements elicitation to confirm and extend the requirements in Section 4.

- Expand the SRS with use case and sequence diagrams and acceptance criteria.

## 11. References

- Market Research Intellect — Smart Parking Platform Market Size and Forecast. Market sizing and key player list.

- Similarweb — SpotHero Competitors, June 2026. Competitive set for garage reservation platforms.

- Unstar — ParkMobile vs SpotHero: 5 Parking Apps Ranked, 2026. Complaint pattern analysis for ParkMobile, SpotHero, PayByPhone, ParkWhiz, and Passport.

- StartupOG — Best ParkWhiz Alternatives & Competitors, 2026. Feature positioning across competitors.

- $oftware ¢orp. — Semester Project: Smart Parking Platform (course project brief).

End of document — version 1.1